## Litigation report
Litigation report 2023.08 | [12 empty] | Active complaint
Claim
Date: | 2023-09-16
Reporting date: | 2023-08-30 | 2023.08
In local currency |  | Buildings
[18 empty] | -407.918 |  | -407.918 | -322 | -322 | 0 | -350 | -479 | -54 | -15 |  |  |  |  | -346.8189
All values in thousands
Situation | [20 empty] | Legal case | [11 empty] | Measures
Division | Country | PC # | IC Name / Name of Investment Center | PSP | Project Description | Project on RDA Yes / No | Type/Nature | Business Responsible | Legal Responsible | Finance Responsible | Case number | Claimant | Respondent of Claim | Counter Party's Relation to Implenia | Status of the Proceeding | Subject matter | Currency | Value in dispute / Claim volume Claim by Implenia (+) / aganist Implenia (-) | Our share % | Value in dispute / Claim volume based on our share | Real Case: Expected enforceable right to payment (+) / enforceable obligation to pay (-) | Considered amount in our accounting | Opportunities (+) / Risks (-) | Accumulated legal costs (expensed) | Expected legal costs (not yet expensed) | Accumulated court costs (expensed) | Expected court costs (not yet expensed) | Date start of proceeding | Date end of proceeding | Date relevant for interest | Interest rate | Interests | Comments | Next Milestone | Date of next milestone / review
Buildings CH | Switzerland | 200017 | Buildings Gros-Oeuvre Ouest | 1000222 | A | No | Expected legal case against Implenia | Peter | Jack | Mathias | 1 | Name A | Name 1 | Client | First Instance - Exchange of briefs | D | CHF | -3000 | 100% | -3000 | -300 | -300 | 0 | 0 | 0 |  |  | 2020-11-30 |  | 2003-08-25 | 5% | -300.411 |  |  | on hold
Buildings CH | Switzerland | 200011 | Buildings VD/Renens | 90003817 | A | No | Expected legal case by Implenia | Max | Nick | Heinz | 2 | Name B | Name 2 | Client | First Instance - Exchange of briefs | D | CHF | -1900 | 100% | -1900 | -800 | -800 | 0 | -45 | -60 |  | -15 | 2016-05-01 |  | 2013-01-01 | 5% | -426.6301 |  |  | on hold
Buildings CH | Switzerland | 200011 | Buildings VD/Renens | 90003817 | A | No | Legal case against Implenia | Heidi | Stella | Rene | 3 | Name C | Name 3 | Subcontractor | First Instance - Exchange of briefs | D | CHF | -100 | 100% | -100 | 0 | 0 | 0 | -7 | -76 |  |  | 2018-01-16 |  | 2013-12-13 | 5% | 0 |  |  | on hold
Buildings CH | Switzerland | 200011 | Buildings VD/Renens | 90003817 | A | No | Legal case by Implenia | Frack | Luna | Simon | 4 | Name D | Name 4 | Subcontractor | First Instance - Exchange of briefs | D | CHF | 860 | 100% | 860 | 0 | 0 | 0 | -7 | 0 |  |  | 2018-01-16 |  | 2013-01-01 | 5% | 0 |  |  | on hold
Buildings CH | Switzerland | 200011 | Buildings VD/Renens | 10000050 | A | No | Legal case against Implenia | Hans | Meike | Marcel | 5 | Name E | Name 5 | Client | First Instance - Exchange of briefs | D | CHF | -3900 | 100% | -3900 | -1000 | -1000 | 0 | -89 | -88 | -4 |  | 2018-01-01 |  | 2014-10-06 | 5% | -445.2055 |  |  | on hold
Buildings CH | Switzerland | 200011 | Buildings VD/Renens | 10000047 | A | No | Legal case by Implenia | Werner | Kerstin | Christian | 6 | Name F | Name 6 | Subcontractor | First Instance - Exchange of briefs | D | CHF | 935.082 | 100% | 935.082 | 568 | 568 | 0 | -33 | -50 |  |  | 2017-03-07 |  | 2015-01-10 | 5% | 245.4071 |  |  | on hold
Buildings CH | Switzerland | 200010 | Buildings Genf/Onex | 10000039 | A | No | Legal case against Implenia | Alexander | Ludwig | Peter | 7 | Name G | Name 7 | Client | First Instance - Exchange of briefs | D | CHF | -30 | 100% | -30 | 0 | 0 | 0 | -47 | 0 |  |  | 2013-01-01 |  |  |  | 0 |  |  | on hold
Buildings CH | Switzerland | 200010 | Buildings Genf/Onex | 10000039 | A | No | Legal case by Implenia | Luisa | Hannes | Max | 8 | Name H | Name 8 | Client | First Instance - Exchange of briefs | D | CHF | 500 | 100% | 500 | 300 | 300 | 0 | -47 | -80 |  |  | 2013-01-01 |  |  |  | 0 |  |  | on hold
Buildings CH | Switzerland | 200030 | Buildings VS/Sion | 90003805 | A | No | Legal case by Implenia | Anne | Julien | Helwig | 9 | Name J | Name 9 | Client | First Instance - Exchange of briefs | D | CHF | 3727 | 100% | 3727 | 950 | 950 | 0 | -65 | -100 | -50 |  | 2011-06-17 |  | 2011-06-17 | 5% | 580.0205 |  |  | on hold
Buildings CH | Switzerland | 200011 | Buildings Crissier | 90003817 | A | No | Legal case against Implenia | Gabriella | Michael | John | 10 | Name K | Name 10 | Client | Evidence preservation proceedings (if not already otherwise pending) | D | CHF | 2500 | 100% | 2500 | -40 | -40 | 0 | -10 | -25 | 0 |  | 2019-12-02 |  |  |  | 0 |  |  | on hold
MOCKUP DATA
HackZurich 2023

## Closed cases
Litigation report 2023.08 | [12 empty] | Active complaint
Claim
Date: | 2023-09-16
Reporting date: | 2023-08-30
In local currency |  | Buildings
All values in thousands
Situation | [20 empty] | Legal case | [11 empty] | Measures
Division | Country | IC # | IC Name / Name of Investment Center | PSP | Project Description | Project on RDA Yes / No | Type/Nature | Business Responsible | Legal Responsible | Finance Responsible | Case number | Claimant | Respondent of Claim | Counter Party's Relation to Implenia | Status of the Proceeding | Subject matter | Currency | Value in dispute / Claim volume Claim by Implenia (+) / aganist Implenia (-) | Our share % | Value in dispute / Claim volume based on our share | Real Case: Expected enforceable right to payment (+) / enforceable obligation to pay (-) | Considered amount in our accounting | Opportunities (+) / Risks (-) | Accumulated legal costs (expensed) | Expected legal costs (not yet expensed) | Accumulated court costs (expensed) | Expected court costs (not yet expensed) | Date start of proceeding | Date end of proceeding | Date relevant for interest | Interest rate | Interests | Comments | Next Milestone | Date of next milestone / review
Buildings CH | Switzerland | 1062 | Buildings Zürich | 12345678 | A | No | Legal case against Implenia | Peter | Jack | Mathias | 123456 | Name A | Name 1 | Authorities | Second Instance - Judgement rendered |  | CHF | -50 | 100% | -50 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | Case closed
Buildings CH | Switzerland | 1010 | Buildings Fribourg | 12345678 | A | Yes | Legal case against Implenia | Max | Nick | Heinz | 654814 | Name B | Name 2 |  |  |  | CHF | -150 | 100% | -150 | -200 | -266 | 66 | 0 | 0 | [6 empty] | 0 |  |  | on hold
Buildings CH | Switzerland | 1001 | Buildings Frauenfeld/SH | 12345678 | A | No | Legal case against Implenia | Heidi | Stella | Rene | 357132 | Name C | Name 3 | Client | Evidence preservation proceedings (if not already otherwise pending) |  | CHF | -120 | 100% | -130 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | on hold
Buildings CH | Switzerland | 1001 | Buildings Frauenfeld/SH | 12345678 | A | No | Legal case against Implenia | Frack | Stephan | Simon | 136845 | Name D | Name 4 | Client | Evidence preservation proceedings (if not already otherwise pending) |  | CHF | -110 | 100% | -110 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | on hold
Buildings CH | Switzerland | 1010 | Buildings Fribourg | 12345678 | A | Yes | Legal case against Implenia | Hans | Meike | Marcel | 365168 | Name E | Name 5 |  |  |  | CHF | -200 | 100% | -200 | -250 | -266 | 16 | 0 | 0 | [6 empty] | 0 |  |  | on hold
Buildings CH | Switzerland | 1062 | Buildings Zürich | 12345678 | A | No | Legal case against Implenia | Werner | Kerstin | Christian | 316413 | Name F | Name 6 | Authorities | Second Instance - Judgement rendered |  | CHF | -50 | 100% | -50 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | Case closed
Buildings CH | Switzerland | 1007 | Implenia Basel | 12345678 | A | No | Legal case by Implenia | Alexander | Wolfgang | Peter | 512183 | Name G | Name 7 | Subcontractor | First Instance - Judgement rendered |  | CHF | 180 | 100% | 180 | 0 | 0 | 0 | -15 | 0 | -4 | 0 |  |  |  |  | 0 |  |  | Case closed
Buildings CH | Switzerland | 1000 | Implenia St. Gallen | 12345678 | A | No | Legal case against Implenia | Luisa | Hannes | Max | 321415 | Name H | Name 8 | Subcontractor | Settlement discussions (inter partes) |  | CHF | -120 | 100% | -120 | -100 | -138 | 38 | 0 | 0 | [6 empty] | 0 |  |  | Case closed
Buildings CH | Switzerland | 1000 | Implenia Zürich | 12345678 | A | No | Legal case against Implenia | Anne | Peter | Helwig | 6542976 | Name J | Name 9 | Subcontractor | First Instance - Judgement rendered |  | CHF | -320 | 100% | -320 | -150 | 0 | -150 | 0 | 0 | [6 empty] | 0 |  |  | on hold
MOCKUP DATA
HackZurich 2023

## Dropdowns
Division | Country | Type/Nature | Counter Partys Realtion to Implenia | Status of the Proceedings | Currency
Real Estate | Austria | Legal case by Implenia | Client | Settlement discussions (inter partes) | CHF
Buildings CH | France | Legal case against Implenia | Subcontractor | Conciliation / ADR proceedings | EUR
Buildings DE | Germany | Expected legal case against Implenia | Supplier | Evidence preservation proceedings (if not already otherwise pending) | NOK
Buildings AT | Norway | Expected legal case by Implenia | Authorities | First Instance - Exchange of briefs | SEK
Civil CH | Romania | Claim |  | First Instance - Court deliberation | RON
Civil DE | Sweden |  |  | First Instance - Judgement rendered
Civil AT | Switzerland |  |  | Second Instance - Exchange of briefs
Civil RO |  |  |  | Second Instance - Court deliberation
Civil NO |  |  |  | Second Instance - Judgement rendered
Civil SE |  |  |  | Third Instance - Exchange of briefs
Civil FR |  |  |  | Third Instance - Court deliberation
SF CH |  |  |  | Third Instance - Judgement rendered
SF DE |  |  |  | Enforcement proceedings
SF AT |  |  |  | Bankruptcy proceedings
SF NO |  |  |  | Expected proceedings
SF SE |  |  |  | Other
SF FR
TUN CH
TUN DE
TUN AT
TUN NO
TUN SE
TUN FR
Specialties
MOCKUP DATA
HackZurich 2023